## Tabelle1
C4PE Feedback Application Testing Protocol
http://37.46.209.90
2020-06-18
Jan Berger
Franziska Grausenburger
Nr. | Testcase |  |  | OK
1 | Log In with an existing user |  |  | x
2 | Sign up / Create a new User |  |  | x
3 | Log Out |  |  | x
4 | Create a new place |  |  | Selecting a place type doesn't chage it from 'cafe'
5 | Search for place |  |  | Only shows results if the full name is entered, problem with the API, replaces spaces in query with '%20'
6 | Filtering for places |  |  | x
7 | Show place page |  |  | x
8 | Create review for / rate place |  |  | x
9 | Rate review for place |  |  | x
10 | Edit review |  |  | x
11 | Edit place |  |  | Editing the place type does not actually change it
12 | Set opening times for place |  |  | The day is always set to Monday
13 | Edit opening times |  |  | Cannot change day
14 | Adding/deleting owners of a place |  |  | x
15 | Update User |  |  | x
16 | Delete place |  |  | Owner can't delete place, but admin can
17 | Create place type |  |  | x
18 | Update place type |  |  | x
19 | Delete review |  |  | No button to delete a review, throws an error on the admin page
20 | Delete user |  |  | x
21 | Visit different pages |  |  | x